## Tasks
Simple Task List
One row per task. Status and priority are drop-downs; overdue work turns red.
Not started | In progress | Blocked | Done | Complete |  | As of | 2026-10-23
4 | 1 | 1 | 2 | 25%
Task | Owner | Priority | Status | Start | Due | Days left | Notes
Define project goals | Alex | High | Done | 2026-09-01 | 2026-09-04 |  | Signed off by sponsor
Draft timeline | Priya | High | Done | 2026-09-03 | 2026-09-09
Collect requirements | Sam | High | In progress | 2026-09-08 | 2026-09-25 | -28 | Two interviews left
Choose vendors | Alex | Medium | Blocked | 2026-09-14 | 2026-10-02 | -21 | Waiting on budget approval
Design review | Jordan | Medium | Not started | 2026-09-28 | 2026-10-09 | -14
Build prototype | Priya | High | Not started | 2026-10-05 | 2026-10-30 | 7
User testing | Sam | Medium | Not started | 2026-11-02 | 2026-11-13 | 21
Launch checklist | Jordan | Low | Not started | 2026-11-09 | 2026-11-20 | 28